## AP
Challenge Categories |  | Area of Improvement | Stream Owner | Priority |  | Planned Actions | Summary | Dashboard Owner | Task Supporters | ECD | Update | Remarks
Customer Data Accuracy | 1 | Geographic-location Correction | Ahmed Fathy | P1 | 1 | 1. Sharing the complete list of all ICCIDs with Azzam. |  | Ahmed Fathy | Ahmed Fathy | Done | Done | Done
Customer Data Accuracy | 1 | Geographic-location Correction | Ahmed Fathy | P1 | 2 | 2. Azzam to share the list and bring the SIM cards accurate locations trough Network team using Pixilization or the beeter accurate tool. | Azzam: Map SIM locations via Network. | Fadil AlZarouni | Azzam | 2026-02-17 | Pending | we shared the 1300 Accounts awaiting their feedback by Tomorrow
Customer Data Accuracy | 1 | Geographic-location Correction | Ahmed Fathy | P1 | 3 | 3. Updating the resulted locations into the Mashup through the data cleansing activity by Ops Team. |  | Ahmed Fathy | Ahmed Fathy | 2026-02-13 | Done | Phase #1 Done 656 Emirates accounts updated
Customer Data Accuracy | 2 | Wrong contact details | Ahmed Fathy | P1 | 4 | 1. Developer contacts to be updated through the security team on-site. | Developer Contacts: Update security team onsite. | Hatem Gado | Hatem Gado | Rejected | Rejected | As Per Hatem rejected from MOI Side with no room for discussion
Customer Data Accuracy | 2 | Wrong contact details | Ahmed Fathy | P1 | 5 | 2. Requesting all customer billing data to validate contact information. | Billing Data: Request customer data validation. | Hatem Gado | Hatem Gado | Rejected | Rejected | No Such Info and he will send the GIS Data only in a few days (Ask Hatem to shre the rejection by MOI and UAE team for the billing info)
Customer Data Accuracy | 2 | Wrong contact details | Ahmed Fathy | P1 | 6 | 3. Validating all individual bills names against the current villa contact details and update the DB with the accurate information. | Billing Names: Sync villa details to DB. | Hatem Gado | Ahmed Fathy | Rejected | Rejected | No Such Info and he will send the GIS Data only in a few days
Customer Data Accuracy | 3 | Mechup/IoT Sync Data Cleansing | Ahmed Fathy | P1 | 7 | 1. Analysis concluded and 1300 Account were found with discrepancy |  | Fadil AlZarouni | Azzam |  | Done | Done
Customer Data Accuracy | 3 | Mechup/IoT Sync Data Cleansing | Ahmed Fathy | P1 | 8 | 2. 1300 Account Communicated to Care to start campaign for Emirate Validation. |  | Fadil AlZarouni | Mohammed Alfalasi |  | Done | Done
Customer Data Accuracy | 3 | Mechup/IoT Sync Data Cleansing | Ahmed Fathy | P1 | 9 | 3. CARE team to provide the timelines for campaign completion |  | Fadil AlZarouni | Mohammed Alfalasi | Thursday, 12 FEB | Done | Done
Customer Data Accuracy | 3 | Mechup/IoT Sync Data Cleansing | Ahmed Fathy | P1 | 10 | 4. List of Accounts is shared with product team to get the location from IT | Account List: Get IT location data. | Fadil AlZarouni | Hatem Gado | 2026-02-16 | Pending | As per Hatem he will share in few days Still pending with Hatem
Customer Data Accuracy | 3 | Mechup/IoT Sync Data Cleansing | Ahmed Fathy | P1 | 11 | 5. Unifing the data source insertion to the HomeSync to ensure the single source of location for the installation. And to automate the emirate selection by using the LAT/LONG information Confirm the admin of the IoT Portal to block the location update using it |  | Amr Fahmy | Amr Fahmy/Ansari |  | Done | The old portal (IoT Portal) is not allowing any data changes from the SRC side
Customer Data Accuracy | 3 | Mechup/IoT Sync Data Cleansing | Ahmed Fathy | P1 | 12 | 6. Automating the location update using IoTSync to retire the account automatically to reflect the location on the Mashup | IoTSync Automation: Automate Mashup location updates. | Ahmed Fathy | Amr Fahmy/Ansari |  | Pending | Moved to phase 2
Customer Data Accuracy |  |  |  |  | 13 | 0. UAT Document to be shared for initiating the Testing | UAT Document: Share for testing initiation. | Fadil AlZarouni | Azzam | 2026-02-13 | Pending
Customer Data Accuracy | 4 | New installation locations update | Ahmed Fathy | P2 | 14 | 1. Testing and confirmation on the managed engine performance | Managed Engine: Test and confirm performance. | Ahmed Fathy | Ahmed Fathy | 2026-02-20 | Pending | Demo conducted for Managed Engine different modules
Customer Data Accuracy | 4 | New installation locations update | Ahmed Fathy | P2 | 15 | 2. Sharing the testing results to IT team with any requirements | Results Sharing: Report findings to IT. | Ahmed Fathy | Ahmed Fathy | TBD | Pending
Customer Data Accuracy | 4 | New installation locations update | Ahmed Fathy | P2 | 16 | 3. Getting the E2E Process flow of the IoT Sync | IoTSync Flow: Get E2E process map. | Ahmed Fathy | Amr Fahmy | 2026-02-18 | Pending | Meting Invite shared for updating the process
Customer Data Accuracy | 4 | New installation locations update | Ahmed Fathy | P2 | 17 | 4. Confirm that the bulk activation is fetching the MOI Reference only without any cahnges in the contact details |  | Ahmed Fathy | Ahmed Fathy | 2026-02-12 | Done | Confirmed only MOI Reference in Both Bulk Retire and Activation
Customer Data Accuracy | 4 | New installation locations update | Ahmed Fathy | P2 | 18 | 5. Ensuring to fulfil all points raised by the testing and optimize the managed engine accordingly | Optimization: Resolve testing points. | Ahmed Fathy | Azzam | TBD | Pending
Customer Data Accuracy | 4 | New installation locations update | Ahmed Fathy | P2 | 19 | 6. New installation loacations to be captured by installation team and updated on the Managed Engine through IoT Sync | New Installations: Capture and sync locations. | Ahmed Fathy | Hatem Gado |  | Pending
Customer Data Accuracy | 4 | New installation locations update | Ahmed Fathy | P2 | 20 | 7. Confirming the final integration of the IoT Sync with the managed engine | Integration: Confirm final IoTSync status. | Ahmed Fathy | Azzam/Mohammed Obied Al Ansari | TBD | Pending | Require the team handover to report under IT/IS Team
Customer Data Accuracy | 4 | New installation locations update | Ahmed Fathy | P2 | 21 | 8. App development to share the process flow to analyze if any room for enhancement is available |  | Ahmed Fathy | Mohammed Obied Al Ansari |  | Done | Shared and we agreed to have weekly meeting to enhance the existing process
Solution Reliability | 5 | Devices JCI Firmware upgrade | Amr Fahmy | P1 | 22 | 1. Getting the approval on the data consumption waiving from UAE business team. | Data Waiving: Obtain UAE business approval. | Amr Fahmy | Amr Fahmy / Salem A Sharif | TBD | Pending | Moved to phase 2
Solution Reliability | 5 | Devices JCI Firmware upgrade | Amr Fahmy | P1 | 23 | 2. Giving the confirmation to Ops team for the upgrade. | Ops Confirmation: Approve upgrade start. | Amr Fahmy | Azzam |  | Pending
Solution Reliability | 5 | Devices JCI Firmware upgrade | Amr Fahmy | P1 | 24 | 3. Plan the updgrade with the vendor and confirm the upgrade timeline | Upgrade Planning: Confirm vendor timeline. | Amr Fahmy | Ahmed Fathy |  | Pending
Solution Reliability | 6 | Auto Ticketing Encancement | Ahmed Fathy | P2 | 25 | 1. Updating all service OPIs to the auto ticketing tool. |  | Ahmed Fathy | Ahmed Fathy/Amr Fahmy | 2026-02-11 | Done | Ready to be deployed, Product Team added to ITSM depended on action point #42
Solution Reliability | 6 | Auto Ticketing Encancement | Ahmed Fathy | P2 | 26 | 2. Product team to add to ITSM |  | Ahmed Fathy | Amr Fahmy / Hatem Gado | 2026-02-12 | Done | awaiting confirmation to start assign any out of warranty tickets to them
Solution Reliability | 6 | Auto Ticketing Encancement | Ahmed Fathy | P2 | 27 | 3. Integrating the new OPIs with the managed engine. | OPI Integration: Integrate with Managed Engine. | Ahmed Fathy | Gupta | TBD | Pending | Pending on other action point
Solution Reliability | 6 | Auto Ticketing Encancement | Ahmed Fathy | P2 | 28 | 4. Implementing the confirmed OPIs with the managed engine. | OPI Implementation: Execute confirmed OPIs. | Ahmed Fathy | Azzam | TBD | Pending | Pending on other action point
Solution Reliability | 7 | Call Center System Unification/Readiness | Ashraf | P2 | 29 | 1. Migrate the SRC team from AVAYA to Genisys as same as Care team (Aligning directly with the technical team) | SRC Migration: Move team to Genesys. | Ashraf Hassan | Ashraf Hassan/EngagedX | 2026-02-18 | In Progress | Meeting scheduled with EngagedX Presales team engaged and meeting scheduled by Tuesday
Solution Reliability |  |  |  |  | 30 | Migration plan to be shared based on the care team requirements | Migration Plan: Align with Care requirements. | Fadil AlZarouni |  | TBD | Pending
Solution Reliability | 7 | Call Center System Unification/Readiness | Ashraf | P2 | 31 | 2. Adding Mashup technical Team with DevOps to the meeting | DevOps Meeting: Add Mashup technical team. | Ashraf Hassan | Ahmed Fathy | 2026-02-17 | Pending
Solution Reliability | 7 | Call Center System Unification/Readiness | Ashraf | P2 | 32 | 3. Complete the full integration of Mashup with Genysis | Genesys Integration: Complete Mashup-Genesys link. | Fadil AlZarouni | Ahmed Fathy/Ashraf | TBD | Pending | Dependent on Genysis migration
Solution Reliability | 7 | Call Center System Unification/Readiness | Ashraf | P2 | 33 | 2. Sharing all call center requiremenets for the CRM system planning. |  | Ashraf Hassan | Ashraf Hassan | 2026-02-13 | Done
Solution Reliability | 7 | Call Center System Unification/Readiness | Ashraf | P2 | 34 | 3. Budget requirement to be prepared for business approval. | Budget Prep: Prepare for business approval. | Fadil AlZarouni | Azzam | 2026-02-16 | Pending
Solution Reliability | 7 | Call Center System Unification/Readiness | Ashraf | P2 | 35 | 4. Business alignment and approval. | Business Alignment: Secure final approval. | Fadil AlZarouni | Hatem Gado | 2026-02-17 | Pending
Solution Reliability | 7 | Call Center System Unification/Readiness | Ashraf | P2 | 36 | 5. New system component integaration and required training for the call center team. | System Integration: Integrate components and train. | Fadil AlZarouni | Azzam | 2026-02-25 | Pending
Solution Reliability | 7 | Call Center System Unification/Readiness | Ashraf | P2 | 37 | 6. ARC/Contact Center Capacity Planning/Hiring |  | Ashraf Hassan | Ashraf Hassan |  | Done
Solution Reliability | 7 |  |  |  | 38 | 7. Hiring Process completion with HR Porteal (Hire&Grow) | Hiring Process: Complete via HR portal. | Ashraf Hassan | Ashraf Hassan/Azzam | 2026-02-17 | Pending | All reuests uploaded to Hire&Grow and pending on Financial approval
Solution Reliability |  |  |  |  | 39 | 8. Adding the DR plan for the call center (Genysis on Prim and ARC) | DR Plan: Setup Genesys/ARC redundancy. | Fadil AlZarouni |  |  | Pending
Solution Reliability | 8 | Field WFSM System readiness | Amr Fahmy | P1 | 40 | 1. Complete requirements to be shared for proposal | Requirements: Share for proposal. | Amr Fahmy | Amr Fahmy | 2026-02-11 | Pending | Moved to phase 2
Solution Reliability | 8 | Field WFSM System readiness | Amr Fahmy | P1 | 41 | 2. Proper solution components to be shared for Business approval. | Solution Components: Submit for business approval. | Amr Fahmy | Azzam | 2026-02-11 | Pending | Moved to phase 3
Solution Reliability | 8 | Field WFSM System readiness | Amr Fahmy | P1 | 42 | 3. Business alignment and approval. | Approval: Align with business stakeholders. | Amr Fahmy | Hatem Gado | 2026-02-12 | Pending | Moved to phase 4
Solution Reliability | 8 | Field WFSM System readiness | Amr Fahmy | P1 | 43 | 4. Implementing the new system, training, and user support. | Implementation: Deploy system and support. | Amr Fahmy | Azzam | TBD | Pending | Moved to phase 5
Solution Reliability |  |  |  |  | 44 | Submitting the requirements for the Auto Ticketing Redundancy | Auto-Ticketing: Submit redundancy requirements. | Fadil AlZarouni |  |  | Pending
Solution Reliability | 9 | System Stability | Amr Fahmy | P1 | 45 | 1. DR for the auto-tecketing (Proposal Submission) | DR Proposal: Submit auto-ticketing redundancy. | Amr Fahmy | Azzam | Pending for Key persons required | Pending | (Gupta, Jaber, and Siv) Required to initiate the plan
Maintenance Readinss | 10 | Capacity Planning | Amr Fahmy | P1 | 46 | 1. Preparing all capacity planning for Ops Team |  | Ahmed Fathy | Ahmed Fathy | 2026-02-10 | Done
Maintenance Readinss | 10 | Capacity Planning | Amr Fahmy | P1 | 47 | 2. Preparing all capacity planning for field operations |  | Ahmed Fathy | Amr Fahmy | 2026-02-10 | Done
Maintenance Readinss | 10 | Finalizing Business Process | Amr Fahmy | P1 | 48 | 1. Submitting the v1.0 process for business dicussion |  | Amr Fahmy | Amr Fahmy | 2026-02-10 | Done
Maintenance Readinss | 10 | Finalizing Business Process | Amr Fahmy | P1 | 49 | 2. Aligning with Business team to amend the process activities effeciently | Process Amendment: Align with business team. | Amr Fahmy | Hatem Gado/Amr Fahmy/Amr Rashwan | 2026-02-12 | In Progress | Product team will set by Monday
Maintenance Readinss | 10 | Finalizing Business Process | Amr Fahmy | P1 | 50 | 3. Updating the last agreed process for managed engine implementation | Process Update: Update Managed Engine implementation. | Amr Fahmy | Amr Fahmy | 2026-02-12 | Pending | Dependent on the managed engine testing
Maintenance Readinss | 10 | Finalizing Business Process | Amr Fahmy | P1 | 51 | 4. Submitting any OPIs, workflows changes that need to be updated on the managed engine | Workflow Changes: Submit OPI/workflow updates. | Ahmed Fathy | Ahmed Fathy | 2026-02-11 | Pending | Moved to phase 2
Maintenance Readinss | 10 | Finalizing Business Process | Amr Fahmy | P1 | 52 | 5. optimizing the changes on the managed engine accordingly | Change Optimization: Refine Managed Engine settings. | Amr Fahmy | Azzam | TBD | Pending | Moved to phase 3
Maintenance Readinss | 10 |  |  |  | 53 | 1. Complete Screening for all received staff to approve them |  | Amr Fahmy | Amr Fahmy/Ahmed Fathy | 2026-02-12 | Done | Done for the Zone Supervisors while the technicians are not ready yet
Maintenance Readinss |  |  |  |  | 54 | Ensure the resources handover with all required access, tools, and materials | Resource Handover: Ensure tools and access. | Hatem Gado |  |  | In Progress
Maintenance Readinss | 10 |  |  |  | 55 | 2. Fulfill all team and start on-ground activities | Field Kickoff: Start on-ground activities. | Amr Fahmy | Amr Fahmy | 2026-02-19 | Pending
Maintenance Readinss | 10 |  |  |  | 56 | 3. Ensure all new stafff Remedy + Managed Engine account creation with the proper group | Account Creation: Setup Remedy/Engine access. | Amr Fahmy | Amr Fahmy/Ahmed Fathy | 2026-02-13 | Pending
Maintenance Readinss | 11 | Resources Onboarding | Amr Fahmy | P2 | 57 | 1. Submitting the required hiring requests by Ops team | Ops Hiring: Submit hiring requests. | Amr Rashwan | Amr Rashwan | 2026-02-17 | Pending | Pending on the current discussion with Business team
Maintenance Readinss | 11 | Resources Onboarding | Amr Fahmy | P2 | 58 | 2. Submitting the required hiring requests by field team | Field Hiring: Submit staffing requests. | Amr Rashwan | Amr Fahmy | 2026-02-13 | Pending | 16 Technicians hiring request raised on Hire&Grow
Maintenance Readinss | 11 | Resources Onboarding | Amr Fahmy | P2 | 59 | 3. Finalizing the Hiring Process with the HR | HR Finalization: Complete the hiring process. | Amr Rashwan | HR Team | TBD | Pending
Additional Actions | 12 |  |  |  | 60 | 1. Validating the mismatched contact details with the new analysis done by Andrew |  | Ahmed Fathy | Ahmed Fathy | 2026-02-12 | Done | 26 Accounts only and updated by Care team
Additional Actions | 12 |  |  |  | 61 | 2. Creating the CR for the Mashup data updating after the validation completed |  | Ahmed Fathy | Ahmed Fathy | 2026-02-13 | Done | Updated
Additional Actions | 12 |  |  |  | 62 | 3. Confirmation on the same with UAE Core team | Core Confirmation: Verify with UAE team. | Ahmed Fathy | Azzam | 2026-02-17 | Pending